# DEMRESAI — Alternative WP Leads, Co-leads, Task Leads & Runtime

Figure 2 (alt): the reshuffled work-package structure, matching the table below.

Principle applied: every WP's Lead + Co-lead(s) are either a mix of Australian and European institutions, or European-only — never Australian-only (exception is WP12 as purely administrative WP. All WPs (beside WP12) must have a very clear public engagement component!

| Work Package | Lead | Country | Co-lead(s) | Country | Task leads | Runtime |
| --- | --- | --- | --- | --- | --- | --- |
| WP1: Framework | Seraphine Maerz (UoM) | Australia | Aurel Croissant (UoH) | Germany | Max Groemping (Griffith), Constanza Sanhueza Petrarca (ANU) | Year 1 (months 0–12) |
| WP2: Media Integrity | Andrea Carson (UoM) | Australia | fact-checking civil-society organisation (tbc) | Europe | Catherine de Kock (UoM), Christopher Leckie (UoM), Janjira Sombatpoonsiri (CU) | Months 6–30 (2 years) |
| WP3: Evidence integrity in policy advice | Max Groemping (Griffith) | Australia | The Good Lobby (Brussels) or rather a public body with a policy-making role? | Belgium | Policy-making institutions (?), Erin O'Brien (Griffith), Janjira Sombatpoonsiri (CU) | Months 6–30 (2 years) |
| WP4: Equitable AI literacy | Tactical Tech | Germany | Tanja Notley (WSU), Kate Williams (UoM) | Australia, Australia | Eric Fu (UoM), a relevant public body with a policy-making role | Months 6–30 (2 years) |
| WP5: Autonomy Paradox | ? (tbc) | Europe | Ed Hovy (UoM) | Australia | Piers Howe (UoM), Yoshihisa Kashima (UoM) | Months 6–30 (2 years) |
| WP6: Citizens Trust | Constanza Sanhueza Petrarca (ANU) | Australia | Marta Kolczynska (UoW) | Poland | Ferran Martinez i Coma (Griffith), Svitlana Chernykh (ANU), Rene Rejon (UoM) | Months 6–30 (2 years) |
| WP7: Deliberative Democracy | Nicole Curato (UoB) | UK | Adele Webb (UoC) | Australia | Nicholas Biddle (ANU), JRC Competence Centre on Participatory and Deliberative Democracy | Months 6–30 (2 years) |
| WP8: AI Governance | Pascal Koenig (VoA) | Netherlands | tbc (Pascal to suggest) | Europe | Evgeny Postnikov (UoM), Andrew Walter (UoM) | Months 6–30 (2 years) |
| WP9: Executive Traceability | Nina Wiesehomeier (IE University, tbc) | Spain | Seraphine Maerz (UoM), Ken Benoit (SMU) | Australia, Singapore | Francesco Bailo (UoS), Sofya Glazunova (UoM) | Months 6–30 (2 years) |
| WP10: Resilience Radar | Steven Wilson (UoG) | Sweden | Carl-Henrik Knutsen (Oslo) | Norway | Aurel Croissant (UoH), Simon Jackman (UoC) | Months 18–30 (1 year) |
| WP11: Findings and Dissemination | Seraphine Maerz (UoM) | Australia | European civil-society organisation as engagement partner (tbc) | Belgium | Max Groemping (Griffith), Constanza Sanhueza Petrarca (ANU) | Months 18–36 (1.5 years) |
| WP12: Project Management | Seraphine Maerz (UoM) | Australia | Project Manager (UoM) | Australia | tbc | Throughout (months 0–36) |

Midterm evaluation: IPU and IDEA (both tbc!)